Report on jointly implemented pilot

action in AT-CZ pilot area

Final Version

October 2025

Table of contents

1

1

1

2

2

2

2

3

3

3

4

4

4

. Introduction .........................................................................................2

.1. About this document ............................................................................2

.2. Accessibility definitions ........................................................................2

. Implementing the pilot action in the AT-CZ area.............................................3

.1. Summary of pilot implementation plan......................................................3

.2. Final status of pilot activities in Weinviertel ...............................................4

.3. Final status of pilot activities in Znojmo region ......................................... 18

. Implemented awareness raising activities ................................................... 33

.1. Event summaries -Weinviertel region...................................................... 38

.2. Event summaries - Znojmo region .......................................................... 42

. Key findings........................................................................................ 43

.1. Weinviertel region............................................................................. 43

.2. Znojmo region .................................................................................. 44

Page 1

1. Introduction

1.1. About this document

This document describes the final jointly implemented pilot action in the cross-border

tourism area Austria-Czech Republic (AT-CZ). The joint report on implemented pilot action is

going to concentrate on finding solutions for improving accessibility in tourism for people

with impaired mobility and vision in the cross-border pilot region AT-CZ (Weinviertel-

Znojmo), based on joint concept testing. It will include summaries of stakeholder workshops.

The contents of this document will be used for finalisation of O2.5 and for planning uptake

(WP3).

1.2. Accessibility definitions

All necessary accessibility definitions like “accessible tourism”, “accessible services and

tools”, “accessible independent travel”, “rural tourism” can be found in the Compendium on

Capacity Building on Territorial Planning for Accessible Tourism, which was prepared in

August 2023 by the project partners BOKU and European Disability Forum (EDF). All detailed

technical requirements for accessibility are collected in the Methodology for Data Collecting,

which also has been prepared during the first reporting period of the CE-Spaces4All project

and was finished in August 2023

Page 2

2. Implementing the pilot action in the AT-CZ area

2.1. Summary of pilot implementation plan

BOKU and Austrian pilot area – Retz region - implemented the following pilot action plan

activities in RP4:

•

•

Presentation of the project at international conferences

Organisation of a special session on the topic of “Invisible Cities” at the ISOCARP

World Planning congress

•

•

Preparation of and literature research for presentations and publications at upcoming

international conferences

Preparations for an awareness raising video which will show the experiences of blind

and visually impaired people on a touristic trip

•

•

•

•

•

•

•

•

Fieldwork - mapping the accessibility of excursion destinations and service providers

Meeting of project parteners in Laa an der Thaya

Summary of hard and soft barriers of the tourism facilities from WAV

Design of a unified format for publishing accessibility information - 3 Manuals

Pilot testing of the Manuals (in progress)

Educating tourism providers about how to create the Accessibility Guide (webinars)

Creating Accessibility Guides of tourism facilities from WAV (in progress)

Leaflet with 6 accessible routes from the pilot area (in progress)

BOKU and Austrian pilot area – Retz region - implemented the following Pilot Action Plan

activities in P5:

•

•

Fieldwork - mapping the accessibility of excursion destinations and service providers

Pilot testing of the Manuals on how to create the Accessibility Guide for customers

with disabilities, including feedback from the tourism providers

•

•

Educating tourism providers about how to create the Accessibility Guide of their

venue

Educating tourism authorities about how to promote publishing of accessibility

information amongst tourism business and support tourism providers to use

Accessibility Guides

•

•

•

•

Consultations and site-visits to assist with creation of the Accessibility Guides at

tourism facilities listed in WAV

Promotion of businesses and service providers who have an accessibility guide on their

websites – listing in a special section on the Weinviertel Tourismus website

Leaflet with 6 accessible routes from the pilot area.Implementation, distribution and

promotion of the leaflet for PWD listing 6 accessible POIs from the pilot area

Marketing – ordering an electric wheelchair for the bike rental shop in Retz to make

the tourist offer more attractive for people with disabilities visiting the region.

Preparing and implementation of the charity run Wings for Life in Retz

Creation of an awareness raising video documenting a day trip to the historic city of

Eggenburg with two visually impaired test persons.

•

•

Page 3

•

Expert meeting with stakeholders from Austrian tourism providers, related

institutions, public transport associations and providers, PWD associations and

Austrian Federal Ministries with project presentation, video premiere, and an

extensive discussion about contents and results.

Czech pilot area - Znojmo region - implemented the following Pilot Action Plan activities in

RP4:

•

•

•

•

•

•

•

Adding new values in WAV to assess soft barriers in accessibility

Summary of hard and soft barriers of the tourism facilities from WAV

Design of a unified format for publishing accessibility information - 3 Manuals

Pilot testing of the Manuals (in progress)

Educating tourism providers about how to create the Accessibility Guide

Creating Accessibility Guides of tourism facilities from WAV (in progress)

Leaflet with 6 accessible routes and 3 POI from the pilot area (in progress)

Czech pilot area - Znojmo region - implemented the following Pilot Action Plan activities in

P5:

•

•

•

Pilot testing of the Manuals on how to create the Accessibility Guide for customers

with disabilities, including feedback from the tourism providers

Educating tourism providers about how to create the Accessibility Guide of their

venue

Educating tourism authorities about how to promote publishing of accessibility

information amongst tourism business and support tourism providers to use

Accessibility Guides

•

•

Consultations and site-visits to assist with creation of the Accessibility Guides at

tourism facilities listed in WAV

Distribution and promotion of the leaflet for PWD listing 6 accessible routes and 3 POI

from the pilot area

•

•

Leaflet for tourism providers/authorities on how to create the Accessibility Guide

Motivational/inspirational video of one hotel from the pilot region, which successfully

applied Accessibility Guide

•

•

Coordinating and facilitating a dialog between students of Mendel University and

Thayatal National Park to develop proposals to remove hard barriers in accessibility of

some parts of the national park (as noted in WAV)

Summary report on the publication of accessibility information of barrier-free tourism

attractions in the pilot area (published on the website of the main tourism authority

in the pilot region)

•

•

Creation of an online resource platform with free instructional materials for tourism

providers on how to create the Accessibility Guide

Adding data from WAV into Znojmo Council mapping portal

2.2. Final status of pilot activities in Weinviertel

Soft barriers in WAV this activity was completed in Period 4:

Page 4

After mapping the accessibility of the tourism facilities in the pilot area, data were saved

and visualized in Web Accessibility Viewer (WAV). These were data on hard/physical barriers

in accessibility. Such attributes were gathered in the previous project periods. Yet there are

also soft barriers in accessing tourism services for PWD - the major one is the lack of

information about available barrier-free services on provider websites. In period 4, the

project team reviewed the websites of all the tourism service providers listed in the WAV, as

well as the newly mapped facilities, destinations and service providers. The website was

checked for information on the accessibility of each facility.in cooperation with project

partners Cenia and the Czech Paraplegic Association, the tool "Accessibility Guide" was

developed and was in P5 put into practice.

Accessibility guide AT

In cooperation with Czech projectpartner was created an accessibility guide for tourism

facility providers. Accessibility Guide (AG) is a summary of basic information about

accessibility of a tourism venue. The AG helps customers with disabilities to evaluate barrier-

free services of the tourism provider, thus significantly improving trip planning. This guide

will help providers easily determine which information is important for people with

disabilities. It was created in CZ and translated into DE. The Manuals were prepared in the

Czech language and translated to German and English for other project partners to use.

Accessible guide was created for accommodation, restaurants and other tourism facilities. It

is used for tourism facilities to put this information on the website to make it easier and

faster for people with disabilities to find a suitable facility. All Manuals are published under

project outputs for free download: https://www.interreg-central.eu/projects/ce-

spaces4all/?tab=outputs (scroll to output: Model for improving mobility of PWD for

independent tourism travel in the transborder tourism area).The materials are also available

on the Weinviertel Tourismus website: https://www.weinviertel.at/accessibility-guide-

leitfaden

Pilot testing of the Manual for creating AG of trip destination

As the Manuals were being created, was tested at excursion destination: themed trail in the

Hollabrunn cellar alley "in the footsteps of the cellar cat". We obtained valuable feedback

from the process, which was used for the Manual improvement. Our first test of AG of

accommodation facility was presented as a case study at online webinars to demonstrate this

Page 5

new approach to other tourism providers in the pilot area. AG is now published on:

Themenweg Sitzendorfer Kellergasse Hollabrunn, NP Thayatal https://www.np-

thayatal.at/de/pages/barrierefreiheit-534.aspx,

Stadt

Retz

https://www.retz.gv.at/de/Tourismus_und_Freizeit/Info_ueber_Barrierefreiheit

Benchmarking analyses of accessibility of tourism facilities in the pilot area

In Period 5, the results of the analysis carried out in the previous period were followed up.

The results served as demonstration material during practical consultation meetings with

tourism service providers, which took place in Period 5.

At period 4, benchmarking analyses of the tourism facilities from WAV were created with

focus on clear display of basic accessibility attributes (hard and soft barriers). All tourism

providers were presented with the results to allow for specific improvements of accessibility

features which transpired as inadequate during the mapping. Three benchmarking analyse

was prepared for accommodation. Simple graphics demonstrated the level of accessibility of

each tourism facility. Benchmarking analyses was also presented at online webinars (below)

as fact sheets to demonstrate the lack of publishing information on accessibility of the

tourism venues in the pilot region (soft barrier in accessibility).

Online webinars for tourism providers

Page 6

Webinars for tourism service providers were held in the previous period (below). In period 5,

face-to-face consultations were held with representatives of businesses and service

providers.

Local tourism service providers needed to be informed about the newly developed

Accessibility Guide tool. Following the example of the Czech project partners, two identical

online tutorial webinars for tourism service providers were held. Invitations to the webinars

were sent out by email and a video invitation was prepared in cooperation with the Czech

project partners: https://interreg-central.eu/wp-content/uploads/2025/02/VID-20250108-

WA0000.mp4

The webinars, entitled Accessible guide - Guide for the disclosure of accessibility on the

website (Accessible guide – Leitfaden für die Offenlegung der Barrierefreiheit auf der

Webseite), presented three guides and gave step-by-step instructions on how to create and

publish AGs on the website. At the same event, the benchmarking (see above) and the use of

WAVs were presented to tourism service providers. The webinars were recorded for future

reference:

2

9. 01. 2025 Accessible guide - Offenlegung der Barrierefreiheit auf der Webseite

6. 02. 2025 Accessible guide - Offenlegung der Barrierefreiheit auf der Webseite

2

Venue: Online, 29. 01. 2025, 26. 02. 2025

Time: 10:00 – 11:00

Organizers: Weinviertel Tourismus

Participants: 31 participants (10 participants PP)

•

•

•

•

Weinviertel Tourism PP: Eva Köllner, Julia Teis

BOKU PP : Tatjana Fischer, Manfred Schrenk

Czech paraplegic association (CZEPA) PP: Marie Scott, Jan Matoušek

Czech Environmental Information Agency (CENIA) PP: Jitka Faugnerová, Vendula

Dastychová, Kateřina Horáková, Martina Sálová

Page 7

Online webinar attendance list:

First

ID

1

Last Name

Facility Name

Date

Email

Name

Weinviertel Tourismus,

Incoming

Melisa

Bartos

29.1.2025 m.bartos@weinviertel.at

2

3

4

5

Romana

Christina

Ilse

Bruckner

Danzer

Hotel freilich

29.1.2025 romana@freilich.at

Weingut Kitla

29.1.2025 Christina.danzer@gmx.at

29.1.2025 i-gritsch@gmx.at

Gritsch

KellergasseführerinDürnleis

Stadtgemeinde Eggenburg

Josef

Gundiger

29.1.2025 Josef.gundinger60@gmail.com

MarktgemeindeNappersdorf-

Kammersdorf

6

Maria

Kappe

29.1.2025 maria.kappe@aon.at

Retzer Land -

7

Silvia

Köhrer

NationalparkThayatalRegiona 29.1.2025 silvia.koehrer@aon.at

lvermarktung

8

9

Robert

Adrien

Johannes

Daniel

Lisa

Köllner

Modre

Pleil

Gemeinde Pernersdorf

Caritas OBENauf Zimmer und

Frühstück

Weinviertel Tourismus

WeinviertlerHeuriger|DasTra

ubenwerk

Gasthaus Matthias Herbst

LEADER Region Weinviertel-

Manhartsberg

29.1.2025 koellner.robert@gmail.com

29.1.2025 adrien.modre@caritas-wien.at

29.1.2025 j.pleil@weinviertel.at

1

1

1

1

0

1

2

3

Seidl

29.1.2025 seidl@weinviertler-heuriger.at

29.1.2025 hanfthal48@gmail.com

Woltran

Zvarikova

Hana

29.1.2025 h.zvarikova@leader.co.at

1

1

1

4

5

6

Manfred

Flora

Breindl

KellergassenvereinHollabrunn 26.2.2025 breindl@mbc.co.at

Buchinger

Gruber

BhW Niederösterreich GmbH

26.2.2025 flora.buchinger@bhw-n.eu

26.2.2025 birgit.gruber@np-thayatal.at

Birgit

NationalparkThayatal

Gemeindedigital, i. V. Oskar

Bayer

1

1

7

8

Peter

Haferl

Schild

26.2.2025 office@haferl.at

robert.schild@hadres.at

Robert

MarktgemeindeHadres

26.2.2025

1

2

9

0

Carina

Scheuer

Schuster

StadthotelHollabrunn

Thermenresort Laa

26.2.2025 hotel@sth-hollabrunn.at

26.2.2025 b.schuster@therme-laa.at

Bettina

Weinviertel Tourismus,

Incoming

2

1

Maria

Susic

26.2.2025 m.susic@weinviertel.at

Agenda:

1

0:00 – 10:05

Welcome

Presentation of accessibility guide

Presentation of WAV and activities in rural areas

Discusion

1

1

1

0:05 – 10:35

0:35 – 10:50

0:50 – 11:00

Description:

The webinar served as a practical tutorial for tourism providers on how and why to create

the Accessibility Guide (AG). Within the framework of the cross-border cooperation in the

pilot area Znojmo - Retz, the format of the webinar for Austrian service providers was

Page 8

adopted from the Czech project partners Cenia and Czepa and adapted for Austrian

conditions.

Project team developed three Manuals, which were presented and reviewed to allow the

attendees to see all its parts: 1st Manual - accommodation, 2nd - restaurant and 3rd - other

tourism attractions. Examples of photographs which should be part of the AG were shown to

the audience and there was a room for practical questions. The webinar presented the case-

study of hotel Premium Znojmo and the excursion destination "Themed Trail in the Footsteps

of the Cellar Cat" in Hollabrunn and, additionally, demonstrated other tourism facilities

locally and abroad which utilize AG online to welcome customers with disabilities. Challenges

which can be faced while publishing the AG on the website were reviewed and a unified

format for publishing the AG was introduced with its logo. The webinars also included

information on how the project partners can assist local tourism providers with AG creation

and publishing. The last part of the webinar focused on presenting the project, including a

demonstration of data mapping, the WAV, and the project's goal of promoting independent

travel for PWDs.

Outcomes of the pilot testing

A total of 21 representatives from various tourist facilities attended the webinars. Several

participants expressed interest in receiving assistance in preparing their Accessibility Guides.

Several participants are already working on the guide and shared their experiences as

examples during the webinar.

The webinars successfully provided tourism operators with practical knowledge on how to

improve accessibility transparency of their venue. The discussions and shared experiences

contributed to an increased awareness of the importance of presentation of clear and unified

accessibility information online. As a result, the initiative is expected to encourage more

businesses to produce AG, ultimately benefiting both PWDs and tourism operators.

The manuals have been published and are freely available on the website:

https://www.interreg-central.eu/projects/ce-spaces4all/?tab=outputs

Information about the webinars was published on the project website:

https://www.interreg-central.eu/news/another-webinar-about-accessibility-guide-this-time-

for-austria/

Page 9

Screenprints from one of the online webinars:

9.1.2025:

2

Page 10

26.2.2025:

Leaflets

The leaflet offers 6 star excursion routes starting from Retz, which are suitable for

passengers with reduced mobility. It was created in cooperation with the tourist information

centres of Retz and Eggenburg. The electronic version is available on the websites of the

Page 11

tourist information centres Retz, Eggenburg, Hollabrunn. On the Czech side, on the websites

of the ZnojmoRegion and the South Moravia Tourism Centre.

In Period 5, the content preparation for the leaflet “Star-trips in the Weinviertel without

barriers” was completed. The leaflet was printed and distributed to tourist information

centers (Retz, Eggenburg, Znojmo), to POIs, and service providers in the region. The leaflet

is also available through the ordering portal of the partner Weinviertel Tourismus. The leaflet

shows six tested trip tips, while other available destinations can be viewed using the QR code

at the bottom of the leaflet. The link leads to the Weinviertel Tourismus website

https://www.weinviertel.at/top-tipps-barrierefreiheit. The content can thus be constantly

updated and expanded with additional offers of available services in the region.

Page 12

Project partner meeting in Rzeszów (PL)

The project partners Weinviertel Tourismus and BOKU participated in a project meeting in

Rzeszów on May 7-8, 2025.

Project partner meeting in Laa an der Thaya:

Project partner Weinviertel Tourismus organized two-day event, scheduled 16th to 17th

October 2024 in reporiting period 4.

The meeting was attended by representatives of all 12 project partners. The aim of the

meeting was to acquaint the project partners with the activities implemented so far and to

ensure the quality implementation of the upcoming activities in the next phases. In the

afternoon, a visit to barrier-free excursion destinations and businesses in the Retz pilot area

took place. During the study visit of the barrier-free facilities the companies were informed

aboutthe progress of the project implementation and project activities.

Page 13

On the second day, the workshop continued with presentations on WP1, WP2 activities,

project management and communication.

Meetings with representatives

In reporting period 4, the project partner Weinviertel Tourismus participated in the

coordination meeting “Strategiegruppe Tourismus in der EU-Dounauraumstrategie”, which

took place on 19 February 2025 in Vienna. In addition to the current developments in the EU

Danube Strategy, the exchange of information on ongoing and completed EU Interreg

projects, initiatives and planned projects and important topics for the coming year was

presented.

Page 14

Charity run Wings for Life

Project partner Weinviertel Tourismus, in cooperation with the city of Retz and project

partners Cenia and CZEPA, organized the Wings for Life charity run and helped promote it in

the region. The event took place on May 4, 2025, in Retz. The CE-Spaces4All project was

presented and promoted during this event.

Page 15

Promo-Wheelchair

Project partner Weinviertel Tourismus purchased a special wheelchair with an additional

electric drive in the 5. period. The choice of wheelchair was consulted with representatives

of project partner CZEPA. The intention to purchase this wheelchair was discussed with

representatives of the town of Retz and a service company (bike rental). The purchase was

consulted with the lead partner and approved. The wheelchair will be located in Retz on the

main square at the bike rental shop and will serve visitors to the city with reduced mobility

to facilitate visits to tourist attractions in Retz and its surroundings. Delivery of the

wheelchair with an additional electric drive is planned for early September 2025.

Video on a touristic trip of blind and visually impaired people

In summer, BOKU started with preparation works for a video showing the experiences of blind

and visually impaired people on a touristic trip to Eggenburg, a medieval city in the border of

Waldviertel and Weinviertel regions. The target group of this video are tourism stakeholders

and spatial planners with responsibility for public infrastructure which is used in tourism. The

video should show them where to pay attention to when acting with and for blind and

visually impaired. It is about demonstrating feasibility and raising awareness.

The elements of the video were orientated towards the travel cycle, which includes all

activities in the course of preparing, carrying out and following up a trip. Visual impairments

are partially shown with visual effects. The viewer should be able to put themselves in the

shoes of the blind or visually impaired holiday maker and understand the journey from their

first-person perspective.

The video was filmed with the support of BOKU’s media department in Eggenburg end of May

2025 after an initial site visit at the beginning of May. The contents of the video are:

•

•

•

•

•

•

•

•

•

•

test persons introducing themselves and explain their visual impairments

arrival of the travellers by train

walk from the railway station towards the city centre

visit of the Krahuletz Museum

visit of the city tourist information office

using a public toilet

visit of the historic city wall

lunch break in a café-restaurant

visit of St. Stephan’s church

walking trip along the historic city wall

While the action itself is filmed without additional comments (i.e. only what the test person

talk to each other was recorded), interrupting sequences feature interview statements from

both test persons about their experiences.

The video was produced in a length of 20-30 minutes and is planned to presented to

representatives of target groups, tourism actors and other relevant stakeholders only in a

moderated and accompanied manner. In the course of such events, the video is embedded in

Page 16

the sequence (1) introduction, (2) video presentation, (3) discussion. Although the production

of the video limits its further usability with regard to accompanied screenings, the scope for

communication with the relevant stakeholders and representatives of user groups is

intensified as a result, and the presentation can be customised. The video was produced in

German. There will be a shorter English version (voice overlay) to be published through the

project’s communication channels

To summary, these activities took place:

Date, place

Topic, title

Stakeholders involved

Page 17

Spring 2025, Retz

and surroundings

Weinviertel Tourismu project

team, CZEPA project team

field work a WAV

Weinviertel Tourismu project

team, CENIA + CZEPA project

team

Spring 2025

Event Wings for Life Run

Video about a trip of

persons with vusual

April/May 2025

BOKU, WVT, City of Eggenburg

impairments to Weinviertel

Final editing, print and

distribution of leaflets with

routes suitable for people

with reduced mobility.

Spring 2025

CENIA project team, Retz

active communication with

tourism service providers to

implement AG on their

websites

Spring + summer

Weinviertel Tourismus project

team

2025

Info day and workshop at

BOKU

July 2025

BOKU

2.3. Final status of pilot activities in Znojmo region

Soft barriers in WAV (activity completed in RP4)

After mapping the accessibility of the tourism facilities in the pilot area, data were saved

and visualized in Web Accessibility Viewer (WAV). These were data on hard/physical barriers

in accessibility. Such attributes were gathered in the previous project periods. Yet there are

also soft barriers in accessing tourism services for PWD - the major one is the lack of

information about available barrier-free services on provider websites (e.g. a hotel offers a

wheelchair accessible bedroom with no information on the website, thus creating a false

impression that the venue offers no barrier-free accommodation). In period 4, the project

team reviewed websites of all the tourism providers listed in WAV to evaluate whether there

is any information about its accessibility available. Four new values were added into the WAV

to assess the current situation: 1.facility has barrier-free services available (often revealed

at site-visit), 2. reference about barrier-free services on the website (e.g. “we offer an

accessible bedroom”), 3. detailed description & photographs of the available adapted

service, 4. detailed description & photographs of all the facilities available at the tourism

venue - Accessibility Guide.

Accessibility guide

Accessibility Guide (AG) is a summary of basic information about accessibility of a tourism

venue. The AG helps customers with disabilities to evaluate barrier-free services of the

tourism provider, thus significantly improving trip planning.

Page 18

Tourism providers often do not know what information to publish online when offering

barrier-free services. Therefore, three Manuals for tourism providers on how to create the AG

were created - 1. accommodation, 2. restaurants and 3. other tourism attractions (e.g.

museums). The Manuals were prepared in the Czech language and translated to German and

English for other project partners to use. All Manuals are published under project outputs for

free

download:

https://www.interreg-central.eu/projects/ce-spaces4all/?tab=outputs

(scroll to output named Model for improving mobility of PWD for independent tourism travel

in the transborder tourism area)

In RP5, more instructional materials for tourism providers were added to an online resource

platform, so that any business can now download all necessary materials free of charge in

order to create its own Accessibility Guide (AG). We created the following instructional

materials:

•

The Manuals on how to create the Accessibility Guide (AG) - accommodation,

gastronomy and tourism attraction

•

•

•

•

•

Icon of AG in colour variations under which the AG is published on provider’s website

Tutorial video with step-by-step guidance on how to create AG

Examples of published AG

Motivational video with tourism provider who explains the process of AG creation

Leaflet for tourism business on how to create AG

Pilot testing of the Manual for creating AG of the accommodation facility

As the Manual for accommodation facility was created, we tested it at The Hotel Premium in

Znojmo. We obtained valuable feedback from the process, which was used for the Manual

improvement. Our first test of AG of accommodation facility was presented as a case study at

online webinars to demonstrate this new approach to other tourism providers in the pilot

Page 19

area. AG is now published on the Hotel Premium website in Czech and English (click on the

wheelchair icon at the main menu next to contacts): https://www.premiumhotel.cz/en/.

In P5, all three Manuals have been used as a template for collecting information about

venue’s accessibility. The project team has been assisting tourism facilities listed in WAV

from our pilot region to use them and are now in a process of collecting valuable feedback.

Here are some examples of AG (Průvodce přístupnosti) published online:

Hotel Happy Star

Hotel Savannah

Krčma a hotel U Císařské cesty

Family City Entertainment Center

Hotel Thaya

Feedback on the use of AG has been collected in the form of qualitative questioning. Tourism

providers listed in WAV with completed AG have been contacted by a telephone and asked

how the AG approach has been working for them. These are question topics being asked:

•

•

•

What did you find easy when creating the AG?

What challenges did you face?

Suggestions for improvements

Benchmarking analyses of accessibility of tourism facilities in the pilot area

At this period, benchmarking analyses of the tourism facilities from WAV were created with

focus on clear display of basic accessibility attributes (hard and soft barriers). All tourism

providers were presented with the results to allow for specific improvements of accessibility

features which transpired as inadequate during the mapping. Three benchmarking analyses

were prepared - 1. accommodation, 2. restaurants (gastronomy) and 3. other tourism

attractions. Simple graphics demonstrated the level of accessibility of each tourism facility.

Benchmarking analyses were also presented at online webinars (below) as fact sheets to

demonstrate the lack of publishing information on accessibility of the tourism venues in the

pilot region (soft barrier in accessibility).

Page 20

In RP5, benchmarking analyses have been used to demonstrate the lack of accessibility

information in tourism, e.g. at online webinar organised for local and regional tourism

authorities on the 10th June.

Online educational webinars

As the new Accessibility Guide (AG) approach needed to be communicated amongst the local

tourism providers, a series of three identical tutorial online webinars for tourism providers

took place. Invitations for the webinar were communicated via various social platforms and

with use of a short video-invitation: https://www.interreg-central.eu/news/czech-austrian-

pilot-region-has-been-testing-accessibility-guides-weibnar-n-2/

At the webinars called How to create an Accessibility Guide for customers with disabilities,

the three Manuals were presented and step-by-step guidance on how to create the AG and

publish it on the website was introduced. At the same event, the tourism providers were

presented with the benchmarking analyses (see above) and use of WAV. The webinars were

recorded for possible future use: https://www.youtube.com/watch?v=NExjE5wAvJo

Participants of the webinars: tourism providers from the Znojmo region identified in WAV +

other tourism providers organized under the Tourism Authority South Moravia (Centrála

Cestovního Ruchu Jižní Morava - CCRJM) and ZnojmoRegion. These stakeholders might be

interested in the results of the pilot actions, which can be expanded outside the Znojmo

region to the entire South Moravia region and beyond. The online setup was chosen due to

the workload of managers of the tourism facilities. Experience from past events has shown

that responsible personnel often cannot attend in person. Three dates in two consecutive

Page 21

months were offered to allow for flexibility while choosing the date of the webinar.

Venue: Online - 10. 12. 2024, 14. 01. 2025, 23. 01. 2025, 10. 06. 2025, 19. 06. 2025

Duration: 60 minutes + time for discussion

Organizers: CENIA and CZEPA

Participants: participants in table below (+ 7 participants PP)

•

•

Czech paraplegic association (CZEPA) PP: Marie Scott, Jan Matoušek

Czech Environmental Information Agency (CENIA) PP: Jitka Faugnerová, Vendula

Dastychová, Kateřina Horáková, Martina Sálová

•

Weinviertel Tourismus PP: Eva Köllner

Online webinars attendance list:

ID First Name

Last Name

Bartíková

Buršík

Červinková

Flechtnerová

Habartová

Facility Name

Hotel Atlantis

Facility type

Accommodation 10.12.2024

Info centre

Info centre

Other

Date

1

2

3

4

5

Veronika

Miroslav

Pavla

Jana

Lenka

Správa Národního parku Podyjí

IC Moravský Krumlov

CZEPA

Galerie mlýn Žeraviny

Regionální muzeum v Mikulově, p.

o. - Archeopark Pavlov

Hotel Happy Star

Jihomoravské muzeum ve Znojmě

Muzeum města Brna, p.o.

Hájenka pod větrníky

10.12.2024

10.12.2024

10.12.2024

10.12.2024

Other

6

Zuzana

Havlická

Other

10.12.2024

7

8

9

Martin

Renata

Šárka

Herzig

Accommodation 10.12.2024

Other

Other

Accommodation 10.12.2024

Other

Hurníková

Klištincová

Kováříková

10.12.2024

10.12.2024

1

1

1

0

1

2

Lenka

Taťána

Patrik

Krajčírovičová Technické muzeum v Brně

Kubát

10.12.2024

10.12.2024

Národní vinařské centrum

Centrála cestovního ruchu – Jižní

Morava

Centrála cestovního ruchu Jižní

Morava

Other

Tourism

Authority

Tourism

Authority

1

1

3

4

Klára

Lepičová

10.12.2024

10.12.2024

Monika

Lidmerová

1

1

1

5

6

7

Kateřina

Irena

Eva

Mrnuštíková

Navrkalová

Oubělická

Maximus Resort

ZnojmoRegion

Brněnsko, z.s.

Accommodation 10.12.2024

Info centre

Info centre

10.12.2024

10.12.2024

Turistické informační centrum

Tišnov

1

8

Barbora

Peterková

Info centre

10.12.2024

1

2

2

2

2

9

0

1

2

3

Veronika

Dana

Tereza

Jan

Procházková

Součková

Tesařová

Zika

AVANTI Hotel

VozejkMap

Dům přírody Moravského krasu

Hotel Vinice Hnanice

Bazén Louka Znojmo

Accommodation 10.12.2024

Other

Info centre

10.12.2024

10.12.2024

Accommodation 10.12.2024

Radek

Sauer

Other

14.01.2025

Accommodation

2

2

4

5

Andrea

Petra

Weisová

Family City

14.01.2025

/

Restaurant

Královéhradecká krajská centrála

cestovniho ruchu, p. o.

SZ Lednice

Vrbasovo muzeum Ždánice

Národní ústav lidové kultury

Bednářová

Info centre

14.01.2025

2

2

2

2

3

6

7

8

9

0

Tomáš

Monika

Marie

Eva

Kollár

Jandorová

Sýkorová

Other

Other

Other

Other

Other

23.01.2025

23.01.2025

23.01.2025

23.01.2025

23.01.2025

Kellner Fialová Zámek Slavkov-Austerlitz

Šimánková Město Mikulov Kultura

Marcela

Page 22

3

3

1

2

Lukáš

David

Agentura průvodců REMO-Agency

Středočeská centrála cestovního

ruchu, p. o.

Other

Tourism

Authority

23.01.2025

10.06.2025

Hanka

Musílková

Tourism

3

3

Eva

Beranová

CzechTourism

10.06.2025

Authority

Info centre

Info centre

Tourism

Authority

Tourism

3

3

4

5

Dana

Martin

Černá

Karas

DMO Kraj blanických rytířů

Královéhradecký kraj

10.06.2025

10.06.2025

3

3

3

3

6

7

8

9

Zuzana

Vojtova

CCRVM

10.06.2025

10.06.2025

10.06.2025

10.06.2025

Centrála cestovního ruchu Východní

Moravy, o.p.s.

Evropská kulturní stezka sv. Cyrila a

Metroděje

Centrála cestovního ruchu Východní

Moravy, o.p.s.

Lenka

Kučerová

Janochová

Valášková

Authority

Martina

Radka

Info centre

Tourism

Authority

Tourism

4

4

4

0

1

2

Lenka

Jitka

Kováčoáv

Destinační společnost Valašsko

MIC Uherské Hradiště

Vysočina Tourism

10.06.2025

10.06.2025

10.06.2025

Authority

Info centre

Tourism

Zálešáková

Merunková

Klára

Authority

Tourism

Authority

Tourism

4

4

3

4

Alena

Lenka

Kudílková

Kováčová

Prague City Tourism

10.06.2025

10.06.2025

Destinační společnost Valašsko

Authority

Centrála cestovního ruchu Východní

Moravy

Spolek Trend vozíčkářů Olomouc

Centrála cestovního ruchu Východní

Moravy, o.p.s.

Tourism

Authority

Other

Tourism

Authority

4

4

4

5

6

7

Petr

Michalec

Macková

Skaunicová

10.06.2025

10.06.2025

10.06.2025

Ludmila

Veronika

Centrála cestovního ruchu Jižní

Morava

Tourism

Authority

4

8

Monika

Lidmerová

10.06.2025

Česká asociace paraplegiků - CZEPA,

z.s.

Česká asociace paraplegiků

Kostel Panny Marie Vítězné a

Pražského Jezulátka

4

5

5

9

0

1

Alena

Vaclav

Marie

Jančíková

Uher

Other

Other

Other

10.06.2025

10.06.2025

10.06.2025

Ambrozková

Tourism

Authority

Tourism

Authority

Tourism

Authority

Other

5

5

2

3

Lucie

Eva

Holásková

Sojáková

Region Slovácko

Region Slovácko

10.06.2025

10.06.2025

Centrála cestovního ruchu Východní

Moravy, o. p. s.

Galerie mlýn Žeraviny

Regionální muzeum v Mikulově,

příspěvková organizace

54

55

56

Veronika

Lenka

Skaunicová

Habartová

Kukla

19.06.2025

19.06.2025

19.06.2025

Tomáš

Other

Tourism

Authority

57

Eva

Sojáková

Region Slovácko

19.06.2025

5

5

6

8

9

0

Lenka

Lenka

Eva

Vlasatá

Kováříková

Kellner Fialová

Resort Ohrada s.r.o.

Hájenka pod větrníky

Zámek Slavkov-Austerlitz

Muzeum Brněnska - Památník

písemnictví

Royal Garden Apartments

Centrála cestovního ruchu Jižní

Morava

Accommodation 19.06.2025

Accommodation 19.06.2025

Other

19.06.2025

61

62

63

Šárka

Dudková

Zýková

Other

19.06.2025

Vladislava

Monika

Accommodation 19.06.2025

Tourism

Lidmerová

19.06.2025

Authority

Page 23

64

65

66

67

68

69

70

Michaela

Blanka

Kristýna

Jana

Andrea

Kamila

Magdalena

Bělinová

Veselá

Králová

Harestová

Musilová

Pokorná

Učňová

Destinační společnost Hradecko, z.s.

MKS Letovice, příspěvková organizace

Benátky 214

Hotel Sladovna

Tree house

Info centre

Other

Accommodation 19.06.2025

Accommodation 19.06.2025

Accommodation 19.06.2025

19.06.2025

19.06.2025

VIDA! science centrum

Muzeum Brněnska

Other

Other

19.06.2025

19.06.2025

Tourism

Authority

71

Hanka

Musílková

Středočeská centrála cestovního ruchu

19.06.2025

Agenda:

5

3

1

1

mins

Welcome

0 mins

5 mins

0 mins

Presentation of Accessibility Guide approach + Manuals

Presentation of WAV and activities in rural areas (not presented 10. 19.6.

Discussion

Description:

The webinar served as a practical tutorial for tourism providers on how and why to create

the AG. The three Manuals were presented and reviewed in its entirety to allow the

attendees to see all its parts. Examples of photographs which should be part of the AG were

shown to the audience and there was a room for specific questions. The webinar presented

the case-study of hotel Premium and, additionally, demonstrated other tourism facilities

locally and abroad which utilize AG online to welcome customers with disabilities. Challenges

which can be faced while publishing the AG on the website were reviewed and a unified

format for publishing the AG was introduced with its logo. The webinars also included

information on how the project partners can assist local tourism providers with AG creation

and publishing. The last part of the webinar focused on presenting the project, including a

demonstration of data mapping, the WAV, and the project's goal of promoting independent

travel for people with disabilities.

In P5, we have created a video-tutorial out of the online webinars. Step-by-step guidance on

how to create the AG in a form of video-tutorial is now available at the online resource

platform with instructional materials for free use for any tourism provider who wishes to

make its accessibility information public. Two educational webinars are being organised at

this monitoring period. One is aimed at all tourism authorities in the Czech Republic

(national, regional, local level). In this webinar, we demonstrated the process of pilot-testing

of the new Accessibility Guide approach. The idea is for the AG to be used by tourism

providers on the national level. Examples of success in our pilot region can motivate tourism

authorities to learn from our experience and utilise our instructional materials all across the

country and beyond. Second webinar is identical to those presented in P4 - in the form of a

tutorial for tourism providers on how to create the AG (more practical).

Summary report on the publication of information on accessibility of barrier-free venues

listed on the website of the main tourism authority in the pilot region

Page 24

Tourism Authority South Moravia (CCRJM) has been active in promoting accessible tourism in

the pilot region for years. It operates an online portal called South Moravia Without Barriers,

where wheelchair accessible tourism attractions are being advertised. As some of the

published venues have not had detailed information on accessibility, the project team

reviewed the website and created a summary of findings. Recommendations for

improvements were discussed with the representative from CCRJM and are now being

transferred into the website.

Outcomes of the pilot testing

A total of 31 representatives from various tourist facilities attended the online webinars. The

webinars successfully provided tourism operators with practical knowledge on how to

improve accessibility transparency of their venue. The discussions and shared experiences

contributed to an increased awareness of the importance of presentation of clear and unified

accessibility information online. As a result, the initiative is expected to encourage more

businesses to produce AG, ultimately benefiting both PWDs and tourism operators.

In RP5, the online webinars’ attendance will be added.

Several participants expressed interest in receiving assistance in preparing the Accessibility

Guides (AG). CZEPA representatives are now in the process of preparing the AG for a number

of local tourism providers in the pilot region - meeting responsible personnel on site to help

with photo-documentation and decision making on what accessibility features to document in

AG. When the AG draft is created, it is followed by a review and clearance for publishing by

the project team.

The three Manuals on how to create the AG have been tested. The Manuals for

accommodation and gastronomy facilities have been tested the most so far. Initially at The

Hotel Premium in Znojmo, where the project team assisted with the whole process (from the

collection of accessibility information according to the Manual, photo-documentation,

transcription of the data into AG format, translation from Czech to English and its publication

on the hotel’s website). Number of other accommodation facilities are now working on their

AG with use of the Manual, tutorial from the online webinar and counselling with the project

team. Screenprints from one of the online webinars:

Page 25

In RP5, the project team conducted the following site-visits with the aim of developing the

AG:

•

•

•

Accommodation facilities - 6

Gastronomy facilities - 8

Tourism attraction - 3

AG published online to the date:

•

•

•

Accommodation facilities - 5

Gastronomy facilities - 1

Tourism attraction - 0

Hotel Happy Star

Hotel Savannah

Page 26

Krčma a hotel U Císařské cesty

Family City Entertainment Center

Hotel Thaya

Hotel Premium

Feedback and experience led the project team to establish an online resource platform for

tourism providers where they can find all materials needed to create the Accessibility Guide.

Here are some statements that businesses shared as feedback:

“It couldn’t have been any easier!” (manager of The Hotel Thaya)

“It’s a good thing, I believe it will help us to attract more customers.” (owner of The Hotel

Happy Star)

“I am not sure why we waited so long for this.” (manager of The Hotel Savannah)

“I would appreciate it if the Accessibility Guide was hosted on an external website and I

could just put a link to it on my website.” (manager of the restaurant Bistrograf)

The summary report with recommendations for improvements in publication of accessibility

information was shared with the representative of the main tourism authority in the pilot

region. It was gladly accepted and used as a guide for amendments.

Meeting with data and GIS experts of Znojmo

Meeting to raise awareness about WAV - focused on data, content, usability for the agendas

of the city of Znojmo. Experts for GIS, city geoportal and spatial planning were contacted

individually as they had not participated in any of the project events organised in Znojmo

since June 2023. There was no official meeting, CENIA team and GIS experts of Znojmo met

at an occasion of two geoinformatics conferences on 23rd September 2024 and 21st

November. Representatives of Znojmo were informed about the activities of the project

activities and possibility of use of the open data coming from the project. CENIA offered to

prepare a web map service (WMS) from WAV data that can be joined to Znojmo geoportal.

(https://mapy.muznojmo.cz/app/index.php?project=katastr_hsl) (under the CENIA – WMS)

Page 27

Meetings with stakeholders

During the reporting period, three key meetings with stakeholders of the Spaces4All project

were held, focusing on strengthening cooperation and coordinating activities in the pilot

area. On 27 March 2025, the project was reintroduced to representatives of Podyjí National

Park in connection with the appointment of the new park director (since February 2025). The

meeting focused on ongoing cooperation, the significant support provided by park rangers

and data specialists in designing accessible routes and conducting field checks, and the

potential organisation of a student workshop by Mendel University to assess the accessibility

of the area and propose possible improvements

On 28 March 2025, a meeting took place with the leadership of the City of Znojmo and the

organisation CZEPA. The project was presented to the newly elected mayor (autumn 2024)

and other city representatives, and current project updates were discussed. These included

the preparation and distribution of leaflets promoting accessible trips, the newly planned

construction of a footbridge in Podyjí National Park, participation of all project partners in

the Wings for Life charity run, and opportunities for cooperation with Mendel University

students

The final meeting was held on 2 May 2025 in Retz with partners from Weinviertel Tourism

and the City of Retz, focusing on the organisational details of the Wings4Life event, including

participant transport logistics and project publicity. The final leaflet with accessible routes

in Znojmo and a draft of similar routes for the Retz area were also presented, reinforcing the

cross-border nature of this activity

All meetings contributed to strengthening collaboration with local partners and ensuring

better dissemination and practical implementation of project outputs.

Leaflet - Znojmo region without barriers

Page 28

A thematic leaflet “Znojemsko bez bariér” (Znojmo Region without Barriers) was prepared

and published. It offers 6 recommended routes and 3 additional points of interest suitable for

travellers with limited mobility in the Znojmo region. The leaflet was developed in

cooperation with local tourist information centres and designed in alignment with the City of

Znojmo’s visual identity to ensure its long-term use and distribution in printed form through

the region’s tourist information centres. An electronic version is available on the websites of

the main regional tourism authorities – ZnojmoRegion (https://znojmoregion.cz/en) and

Tourism Authority South Moravia (https://www.jizni-morava.cz/cz/vylety-bez-barier/) – and

can also be downloaded free of charge from the project partner CZEPA’s website (leaflet

link). In project period 5, the leaflet was printed, distributed among local TICs, and actively

promoted via social media targeting persons with disabilities. The leaflet contributes to

better awareness of available accessible routes and strengthens the practical impact of the

project in the pilot area

Leaflet - Accessibility Guide for tourism providers

In P5, the project team created another leaflet, this time aiming at tourism providers. The

leaflet summarises advantages of the Accessibility Guide (AG) and states the process of

creating one - QR code takes the reader to the online resource platform.

Page 29

Cooperation with MENDELU

The Spaces4All project connects Mendel University, CENIA, Podyjí National Park, the

Weinviertel region, and the Czech Paraplegic Association (CZEPA) to improve accessibility of

public spaces for all, particularly people with limited mobility. In May 2025, a series of field

workshops began with an introductory meeting at MENDELU’s Faculty of Horticulture.

Students then joined experts in the field to experience nature alongside a wheelchair user,

identifying barriers and challenges.

They conducted detailed analyses of two locations – Havraníky and Čížov – focusing on trail

adjustments, viewpoints, shelters, furniture, and the information system. Proposals included

new barrier-free paths, a three-level trail classification (blue, red, black), sensitive

architectural solutions for viewpoints and footbridges, and accessible toilets and parking.

The information system would feature QR codes with audio recordings and tactile elements

for visually impaired visitors.

The aim is to remove physical barriers and create a safe, logical, and attractive trail

network, allowing all visitors – regardless of physical ability – to move through Podyjí National

Park comfortably and with dignity.

Page 30

To summarize, these activities took place:

Date, place

Topic, title

Stakeholders involved

Spring 2025,

Znojmo and

surroundings

CENIA project team, CZEPA

project team

field work for WAV

CENIA project team, CZEPA

project team, Tourism Authority

South Moravia (CCRJM),

ZnojmoRegion, tourist information

centres in Znojmo

Final editing, print and

distribution of leaflets Znojmo

region without barriers

Spring 2025

Promo campaign in Znojmo for

the Wings4Life run in Retz.

Presentation of the project at

information stand (roll-up,

distributions of leaflets with

maps of accessible trips)

CENIA project team, CZEPA

project team, Weinviertel team,

BOKU team, Tourism Authority

South Moravia (CCRJM),

ZnojmoRegion, tourist information

centres in Znojmo, Retz

4.5.2025

Provide summary of the online

advertising of barrier-free

destination offers in the pilot

area - this will be based on the

review of the main tourism

authority websites - CCRJM.

Tourism Authority South Moravia

(CCRJM), tourist information

centres in Znojmo, CENIA project

team, CZEPA project team

Spring -

summer 2025

Page 31

Date, place

Topic, title

Stakeholders involved

Evaluation of usability of WAV

data for the application

Spring –

summer 2025

https://www.vozejkmap.cz

(managed by CZEPA). Transfer

of suitable data, translation to

English) in progress

CENIA, CZEPA

Offer solution to hard barriers

in accessibility in National Park

Podyjí - inaccessible viewing

point Iron Trails, inaccessible

resting cabins - see more below

in progress

Administration of the National

Park Thayatal- Mr. Bursík and his

team, CENIA & CZEPA project

team, Mendel University Brno -

Institute of Landscape Planning

May 2025

Assistance with creation of

Accessibility Guides for tourism

providers in pilot region

Spring -

Autumn 2025

CENIA project team, CZEPA

project team

CCRJM, ZnojmoRegion, other

regional tourism authorities (e.g.

Tourism Authority the Hradec

Králové region), CzechTourism?,

CENIA project team, CZEPA

project team

Introducing Accessibility Guide

approach to a wider group of

service providers in tourism

June 2025

Office of the Government of the

Czech Republic - Committee of

the Government Council for

Persons with Disabilities for the

Accessibility of Public

Proposal for the introduction of

a general information

obligation regarding the

accessibility of services

July 2025

Administration and Public

Services, CZEPA

CENIA project team, CZEPA

project team, Znojmo town,

CCRJM, ZnojmoRegion,

CzechTourism

Leaflet to popularize AG

concept for tourism facilities

August 2025

Page 32

3. Implemented awareness raising activities

These awareness-raising activities have been held in the AT-CZ pilot area during reporting

periods 4 and 5. The most important events are listed below and there is a short summary of

these events in this chapter.

Weinviertel

Date, place

Topic, title

Stakeholders involved

Weinviertel Tourismus in

cooperation with CENIA project

team and CZEPA project team

Creating an accessibility guide for

tourism facility providers

09. 2024

2

Bali

(Indonesia),

virtual

attendance

-3 Sept 2024,

project presentation at World

Disability and Rehabilitation

Conference (WDRC), paper title:

Travel Behavior and Experiences

of Persons with Disabilities Living

in Austria – Findings from an

Online-Survey

BOKU project team

2

-6 Sept 2024,

project presentation at WMCCAU

conference, paper title: The Web

Accessibility Viewer: a Tool to

Assist Travelling Persons with

Disabilities

BOKU project team

BOKU project team

Ostrava (CZ)

8-12 Oct

Special session at ISOCARP World

Planning Congress, topic:

2024, Siena

(IT)

Inclusive INVISIBLE CITIES – How

to deal with blindness and visual

impairments in Urban and

Regional Planning?

Study visit – tourism providers

from the Retz region.

Project partner meeting in Laa an der

Thaya

10/2024

Benchmarking analyse- creation of

overview with visually clear and

simple evaluation of hotels.

Evaluation based on accessibility

catalogue - mapping in the pilot

area and its data transcription

into WAV.

1

1

1/2024 -

2/2024

Tourism providers from the Retz

region identified in WAV + new

Tourism providers from the

Austria site of the pilot region

where mapping of accessibility

took place and its results were

saved in the WAV database.

Telephone consultations with

tourism providers from the pilot

area where mapping took

place/WAV database

11/2024

Page 33

Weinviertel Tourismus, CENIA

project team, CZEPA project

team. Developed in cooperation

with Retz information centre

Creation of texts for a leaflet

with routes suitable for people

with reduced mobility.

12/2024

Weinviertel Tourismus, CENIA,

CZEPA, tourism providers from

Retz region identified in WAV +

any tourism provider in

Weinviertel (Retz + Eggenburg -

area)

Online webinar for tourism

providers - what and how to

publish info on accessibility -

Accessibility Guide

2

9 Jan 2025,

online

Weinviertel Tourismus, CENIA,

CZEPA, tourism providers from

Retz region identified in WAV +

any tourism provider in

Online webinar for tourism

providers - what and how to

publish info on accessibility -

Accessibility Guide

2

6 Feb 2025,

online

Weinviertel (Area Retz,

Hollabrunn, Laa, Poysdorf)

Conference "Strategiegruppe

Tourismus in der EU-

Dounauraumstrategie"-

Weinviertel Tourismus + BOKU

project team + implementers of

Interreg projects in area EU-

Danube.

information about the project,

raising awareness, finding

potential partners for pilot

events. Acquiring new contacts

for further cooperation, building

networks and capacities.

19 Feb 2025

communication with service

providers - implementation of

accessibilty guide on service

providers' websites

Weinviertel Tourismus + service

providers in pilot area Retz

Spring 2025

03-

0

5,08/2025,

Weinviertel Tourismus project

team, CZEPA project team

field work for WAV

Retz and

surroundings

Weinviertel Tourismus project

team, CENIA project team,

CZEPA project team, tourist

information centres in Retz,

Hollabrunn, Eggenburg and

Haugsdorf, NP Thayatal,

Preparing, editing, production

and distribution of leaflets “Star

trips in Weinviertel without the

barriers”

0

4-08/2025

4-05/2025

preparation for implementation

for the charity run Wings4Life in

Retz (4.5.2025). Presentation of

the project at information stand

Weinviertel Tourismus team,

CENIA project team, CZEPA

project team, BOKU team,

Tourism Authority South Moravia

0

Page 34

(roll-up, distributions of

information about project

(CCRJM), ZnojmoRegion, tourist

information centres in Retz,

Znojmo, town Retz, running

clubs from Retz and Znojmo

“Bildung hat Wert” - information

about the project, raising

awareness, finding potential

partners for pilot events.

Acquiring new contacts for further

cooperation, building networks

and capacities.

Weinviertel Tourismus team +

implementers of Interreg

projects

0

6/2025

/2025 -

Consultations and sites visits at

tourism facilities listed in WAV to

assist with creation of the AG

3

Weinviertel Tourismus team,

local service providers

ongoing

Weinviertel Tourismus team,

project partners CZEPA and LP

GI of Slovenia,participans of

Retz municipality, tourist

information centre Retz and

bike rental,

Wheelchair with additional

electric drive – preparation of

purchase and purchase

07-08/2025

Presentation of the project and

project results during the expert

conference

"

FachgesprächLändlicher

Weinviertel Tourismus team, PP

BOKU, stakeholders of project

area.

Tourismus für Sehbeeinträchtigte"

(Expert Discussion on Rural

Tourism for the Visually

08 July 2025

Impaired), organized by project

partner BOKU in Vienna on July 8,

2025.

Znojmo region

Date, place

Topic, title

Stakeholders involved

Designing a unified format for

publishing accessibility information

online - 3 Manuals for tourism

providers on how to create

Accessibility Guide

CENIA project team, CZEPA

project team

0

9 - 11/2024

1 - 12/2024

CZEPA, CENIA, hotel Premium in

Znojmo

Testing the Manual for

accommodation at hotel Premium

1

Page 35

Benchmarking analyses - creation

of overview with visually clear

and simple evaluation of 1.

1

1

1/2024 -

2/2024

hotels/2. restaurants/3. other

tourism attractions. Evaluation

based on accessibility catalogue

Tourism providers from the

Znojmo region identified in WAV

-

mapping in the pilot area and

its data transcription into WAV.

Tourism providers from the

Czech site of the pilot region

where mapping of accessibility

took place and its results were

saved in the WAV database.

Telephone + email consultations

with tourism providers from the

pilot area where mapping took

place/WAV database.

1

0

1/2024 -

1/2025

Meeting for raising awareness

about WAV – aiming at data,

content, usability for agendas of

the city of Znojmo.

0

9 and

CENIA, representatives of

Znojmo

11/2024

Conference Inspirujme se -

information about the project,

raising awareness, finding

21. 11. 2024

potential partners for pilot

events. Acquiring new contacts

for further cooperation, building

networks and capacities.

CENIA project team

CENIA project team, CZEPA

project team. Developed in

cooperation with Znojmo

tourism information centres.

Creation of texts for a leaflet

with routes suitable for people

with reduced mobility.

1

0

1/2024 -

2/2025

CENIA, CZEPA, Weinviertel,

tourism providers from Znojmo

region identified in WAV +

tourism providers organised

under Tourism Authority - South

Moravia (CCRJM) +

Online webinar for tourism

providers - How to create the

Accessibility Guide for

1

0. 12. 2024,

online

customers with disabilities.

ZnojmoRegion + any tourism

provider in South Moravia and

beyond - advertising on social

media.

Page 36

CENIA, CZEPA, Weinviertel,

tourism providers from Znojmo

region identified in WAV +

tourism providers organised

under Tourism Authority - South

Moravia (CCRJM) +

Online webinar for tourism

providers - How to create the

Accessibility Guide for

1

4. 01. 2025,

online

customers with disabilities.

ZnojmoRegion + any tourism

provider in South Moravia and

beyond - advertising on social

media.

CENIA, CZEPA, Weinviertel,

tourism providers from Znojmo

region identified in WAV +

tourism providers organised

under Tourism Authority - South

Moravia (CCRJM) +

Online webinar for tourism

providers - How to create the

Accessibility Guide for

2

3. 01. 2025,

online

customers with disabilities.

ZnojmoRegion + any tourism

provider in South Moravia and

beyond - advertising on social

media.

0

5/2025,

CENIA project team, CZEPA

project team

Znojmo and

surroundings

field work for WAV

CENIA project team, CZEPA

project team, Tourism Authority

South Moravia (CCRJM),

ZnojmoRegion, tourist

information centres in Znojmo

Final editing, print and

distribution of leaflets Znojmo

region without barriers

3

0.04.2025

4.05.2025

CENIA project team, CZEPA

project team, Weinviertel team,

BOKU team, Tourism Authority

South Moravia (CCRJM),

ZnojmoRegion, tourist

Promo campaign in Znojmo for

the Wings4Life run in Retz.

Presentation of the project at

information stand (roll-up,

distributions of leaflets with

maps of accessible trips)

0

information centres in Znojmo,

Retz

Provide summary of the online

advertising of barrier-free

destination offers in the pilot

area - this will be based on the

review of the main tourism

authority websites - CCRJM.

Tourism Authority South Moravia

(CCRJM), tourist information

centres in Znojmo, CENIA

project team, CZEPA project

team

06/2025

Page 37

CZEPA, tourism providers from

the pilot region where mapping

of accessibility took place and

its results are kept in the WAV

database.

Consultations and sites visits at

tourism facilities listed in WAV

to assist with creation of the AG

3

/2025 -

ongoing

Online meeting with Tourism

Authority South Moravia (CCRJM)

to discuss results of the report

on publication of access.

information of their listed

venues

0

1.04.2025

6.05.2025

CENIA, CZEPA, CCRJM

Administration of the National

Park Thayatal - Mr. Bursík and

his team, CENIA & CZEPA

project team, Mendel University

Brno - Institute of Landscape

Planning

Offer solution to hard barriers in

accessibility in National Park

Podyjí - inaccessible viewing

point Iron Trails, inaccessible

resting cabins

1

Online webinar for organizations

in tourism (national, regional,

local level)

CENIA, CZEPA, Tourism

Authorities in the Czech

Republic

1

0.06.2025

9.06.2025

Online webinar for tourism

providers - How to create the

Accessibility Guide for customers

with disabilities.

CENIA, CZEPA, tourism providers

from the Czech Republic

1

CENIA project team, CZEPA

project team, Znojmo town,

CCRJM, ZnojmoRegion,

CzechTourism

Leaflet to popularize AG concept

for tourism facilities

06/2025

3.1. Event summaries -Weinviertel region

This chapter features short summaries from the most important events and workshops in the

lists above.

Online webinars

According to the Austrian Federal Disability Act, a disability is defined as the effect of a non-

temporary physical, mental or psychological impairment that makes it difficult to participate

in social or working life. According to a survey conducted by Statistics Austria in 2015 as part

of the micro-census, 18.4% of the population were affected by disabilities. Permanent

disabilities are strongly age-dependent, so this figure is constantly rising as society ages,

making it more important to make tourism, leisure, and recreational activities accessible to

this section of society.

Page 38

Project presentation at WMCCAU 2024 conference: paper publication

According to the Austrian Federal Disability Act, a disability is defined as the effect of a non-

temporary physical, mental or psychological impairment that makes it difficult to participate

in social or working life. According to a survey conducted by Statistics Austria in 2015 as part

of the micro-census, 18.4% of the population were affected by disabilities. Permanent

disabilities are strongly age-dependent, so this figure is constantly rising as society ages,

making it more important to make tourism, leisure, and recreational activities accessible to

this section of society.

The EU-Interreg funded project CE-Spaces4All aims at the improvement of accessibility of

tourism for persons with disabilities, concentrating on three groups with different

requirements: persons with mobility impairments (wheelchair users), blind people and

persons with visual impairments, deaf people and persons with hearing impairment. Public

authorities, tourism development stakeholders and persons with disabilities from seven

countries are working together in three European pilot regions (Poland, Austria/Czech

Republic, Slovenia/Croatia/Hungary) in a capacity building process to improve conditions for

accessible tourism development and independent tourism travel. A key element of the

project is the Web Accessibility Viewer (WAV) which serves as a data-driven platform for

recording and visualizing architectural, communication and other barriers, for developing

tourism strategies and spatial planning, and for developing tools and services for persons

with disabilities. The project partners organised field mapping events to capture barriers on-

site in the pilot regions and record them on a map.

The WAV is a Geographic Information System (GIS) based online service with a desktop and a

mobile application based on QGIS open source software to collect data according to a joint

catalogue of barriers developed together with the European Disability Forum, an umbrella

organisation of persons with disabilities that defends the interests of over 100 million persons

with disabilities in Europe. The WAV comprises tourism-related barriers (for example parking,

paths, public transport, tourism facilities, points of interest) from all pilot regions

categorised by the three groups of persons with disabilities mentioned above supplemented

by an easy-to-understand accessibility assessment with a semaphore system (red: not

accessible, orange: partly accessible, green: accessible). Photos of the mapped spots are

taken by the respective mapping teams and directly linked with the datasets. The WAV is

available in English as well as all the national languages of each project partner country.

Work with the WAV subsequently resulted in a catalogue of barriers that serves as a starting

point for further measures, for example for action plans for long-term territorial cooperation

on improving accessibility of the pilot regions. Awareness raising events with local and

regional stakeholders complement the agenda of sensitising institutions, companies and

public administration related with tourism. This will lead towards a better governance for

policy and territorial planning of accessible tourism as well as improvement of public services

for persons with disabilities.

Project presentation at WDRC conference

Page 39

Independent travel and access to leisure activities for persons with disabilities (PWD) are

both at the heart of the EU Strategy for the Rights of Persons with Disabilities 2021-2030. A

review of efforts in this regard reveals that tourism planning tends to focus on physical

accessibility of buildings. Comparatively little attention is paid to low-barrier travelling and

mobility on site. As part of the project “Accessible Spaces for All – Improving the Accessibility

of Tourism for Persons with Disabilities in Central Europe” primary data on the travel

behaviour and experiences of PWDs will be compiled. A questionnaire headed by the

European Disability Forum was set up in English language and translated into the national

languages of the project partners. In Austria, 40 national institutions, associations and PWD-

organisations as well as selected stakeholders (individual persons)were asked to support the

data collection and to distribute the link to the Microsoft Forms bilingual questionnaire via

their communication channels in order to reach not only their members living in Austria, but

also interested persons from abroad. As of March 2024, 29 respondents filled in the

questionnare; 23 persons disclosed Austria as place of residence. 9 respondents are female

and two thirds of the respondents older than 55 years, either physically or visually impaired.

For this is work in progress, the results of the descriptive data analysis using SPSS reveal the

following: about half of the respondents travel 3 to 5 times a year, mainly accompanied by

family members. Domestic and international trips are carefully planned in advance.

Accessible websites of booking platforms, recommendations, the destinations’ compliance

with accessible labels and cancellation options are important factors when planning the

journey. A lack of information on accessibility along the journey is a focal commonly

perceived barrier while traveling. Positive travel experiences increase the probability of

revisiting the destination. Based on the findings from strategies on accessible tourism and

good practice examples in Austria on the one hand and the preliminary results of the online-

survey analysis on the other hand, we understand that there is plenty room for improvement

regarding “all-round tourism packages” for PWD in Austria. A consolidation of all survey data

collected by the project partners is planned in order to find out whether and to what extent

(Austrian) rural regions may become a (more) appealing (international) travel destination for

PWD.

Special session at ISOCARP World Planning Congress

There are many people for whom cities are “invisible” in the literal sense of the word - blind

and visually impaired persons. Cities can be “invisible” but still with their fabric, their flair,

their amenities they can be very attractive for people with disabilities, even for blind and

visually impaired ones. How to make cities and regions barrier free and accessible (a

challenge especially in historic surroundings) and inclusive (including the human interactions,

e.g. qualified staff in hotels and restaurants, public institutions, awareness in general public)

and let those persons have a chance to experience, feel and enjoy the cities and regions.

Some supportive technologies might be installed in cities - but what about the areas outside

the urban conurbations - in rural areas, small towns, villages. Even though there are UN- and

EU acts and guidelines, it seems that the needs and RIGHTS of persons with disabilities are

hardly a major topic in urban and regional planning yet.

The implementation of guidelines like the UN Convention on the Rights of Persons with

Page 40

Disabilities or the EAA - European Accessibility Act into national laws and urban planning

practice will be an important part of the discussion. Blindness and visual impairment are only

one segment to deal with when talking about persons with disabilities - mobility impaired

persons, especially wheel-chair users might be more "visible" – but there is a wide range of

disabilities, and average statistics say that about 15-20% of the population are facing

disabilities - this is a topic that should not be neglected in Urban and Regional Planning.

The intention of the special session is to bring representatives of associations of people with

disabilities in contact with the “international urban and regional planning scene”, as it is

represented by ISOCARP - to raise awareness and mutual understanding, in best case even

find ways to work together in a structural way or on project basis.

Paper submission and presentation at WMCCAU 2025 conference

A paper on CE-Spaces4All titled “Creating Spaces for All: From Mapping the Barriers towards

Accessible Tourism” was accepted for presentation and publication at WMCCAU 2025

conference in Ostrava, Czech Republic, which takes places from 1 to 5 September 2025.

The paper comprises highlights from two and a half years of project experience. From the

first project idea generation over data collection, and implementation of tools and services

the paper presents the path to raising awareness using two examples from the sub-pilot

regions of Austria (video of a trip to Eggenburg) and Slovenia (Accessible Pomurje Region),

outlining the key points of the planned measures and the achievements reached with these

measures.

The paper “analysed which measures are effective in facilitating access to rural tourism for

persons with disabilities. During the work on the CE-Spaces4All project, it emerged that the

difficulties are mainly to do with a lack of information (so-called soft barriers). Many tourist

facilities are fully or partially accessible, as the data collection for the Web Accessibility

Viewer revealed.

Rather, it is the lack of information that represents one of the main barriers, in two different

aspects:

•

persons with disabilities are unable to adequately prepare themselves in the course of

their travel preparations because they are unable to find information on whether the

desired destinations or the desired tourism attractions and tourism offers are actually

accessible to the extent that is necessary for them,

•

tourism providers are not sufficiently prepared as to how they should prepare

information on accessibility so that this information can be interpreted and correctly

assessed by persons with disabilities.

The project is working on eliminating these gaps and other barriers in order to ultimately

turn rural spaces into spaces for all in terms of tourism.” (source: Beyer et al., Creating

Spaces for All: From Mapping the Barriers towards Accessible Tourism. In: Proceedings of

WMCCAU 2025 conference, 2025, [currently] unpublished).

Page 41

3.2. Event summaries - Znojmo region

Webinars

Online webinars for tourism providers on how to create Accessibility Guide (AG) have been

the main channel to introduce this new concept. When preparing the events, the project

team focused on the content to be in the form of a simple step-by-step tutorial aiming to

have attendees able to construct the AG themselves upon completion of the webinar.

Presenting examples of the completed AG on the website of a local tourism provider from

Znojmo (hotel Premium) proved to be very motivational. Case-study of the actual process of

AG production and online publication at hotel Premium demonstrated how this new concept

can be simple and straightforward with use of the Manuals. Number of tourism providers got

in touch after the webinars and requested consulting and/or assistance with AG production

for their venue.

Positive feedback from tourist service providers was expressed already at the webinar. They

appreciated the length of the webinar (60 minutes), the presenters, mainly M. Scott who

explained clearly the needs of PWD and the practical examples. Online surveys were

distributed after each webinar with a return rate about 30%. The answers from the survey

evaluated positively the content of the webinar. Some of the tourist service providers were

willing to create the Accessibility guide of their facility after the webinar.

In P5, the project team focused on incorporating the feedback and past experience to make

the process of creation of the AG as easy as possible for all interested tourism providers.

Online resource platform was set up as a place where the necessary instructional materials

can be found free of charge. Online webinar for tourism providers has the same structure of

step-by-step tutorial on how to create the AG. Some parts were adjusted, e.g. online

resource platform with new materials, more examples of tourism venues from the pilot

region. One new online webinar was put together at this monitoring period - Accessibility

Guide - publishing information on accessibility of tourism venues. This webinar was presented

to tourism organizations across the country, thus promoting the new AG concept beyond the

borders of the pilot area.

Telephone and face-to-face consultations with local tourism providers

Personal communication with tourism providers transpired to be one of the most crucial parts

of the pilot testing of the AG approach in the area. Most managers do not read emails from

unknown senders or ignore electronic invitations all together. Therefore, each tourism

provider where mapping of accessibility took place earlier in the project, were spoken to via

telephone or in person (CZEPA’s project team member resides in the pilot area).

The structure of the phone calls/face-to-face were as follows:

•

providing positive and venue-specific feedback from the mapping of accessibility

(most tourism facilities provide services for PWDs) + referring to the benchmarking

Page 42

analysis sent to them via email previously for a full review of the detailed

accessibility assessment of their place.

•

explaining what a loss of business opportunity it is to have such a wonderful barrier-

free venue yet not advertising it on the website, thus falsely presenting itself as non-

accessible.

•

•

brief explanation of what Accessibility Guide is and how it benefits customers with

disabilities and businesses in tourism.

invitation to an online webinar to get hands-on tutorial on how to create AG for their

venue + how and where to get assistance from the project team.

In RP5, the project team carried on in personal communication with tourism providers in the

pilot region. Number of providers attended our online webinars and asked for assistance with

the creation of their AG. Number of site-visits took place and CZEPA’s representatives

supported the tourism facilities in production of the AG - see above.

4. Key findings

This chapter collects text parts which underline the outcomes of these events and what we

learned for the project. It also lists first solutions with the implementation of the services

and tools or first ideas how the results will be integrated in WP3.

4.1. Weinviertel region

Tourism providers in the Retz region appear to be keen on publishing information about

barrier-free services they provide once they are given clear guidance - The Manuals on how

to create the Accessibility Guide (AG). Majority of the tourism providers from WAV preferred

hands-on assistance with production of the AG (on-site meeting of the facility’s manager with

a member of the project team, assistance with photo-documentation/following up The

Manual, transcription of data into AG format).

The aim is to make the AG concept more widely known to local tourism providers. Free

manuals are available on the project website and can be used by tourism businesses. In the

future, it will be crucial how many service providers implement AG on their websites. It will

also depend on the willingness to adopt the AG approach at regional/national/international

level. Weinviertel Tourismus supports the AG approach and will promote it through its online

channels.

Personal communication with the responsible staff of tourism service providers improves the

results of the pilot project activities.

A lack of information on accessibility along the journey is a focal commonly perceived barrier

while travelling. This was our main intent for producing a video that exactly covers this

topic.

There are several publications, for example from the Austrian Federal Economic Chamber, on

accessibility in tourism. However, what these well-designed brochures have in common is

that the group of blind and visually impaired people is underrepresented or not represented

Page 43

at all.

The state of accessibility in rural areas is sometimes challenging and still requires many

different activities. With our agendas, we can offer tourism stakeholders valuable support in

finding a position and self-determination. It is important to make stakeholders aware that

even a few small, easy-to-implement steps can be a great help.

4.2. Znojmo region

Tourism providers in the Znojmo region appear to be keen on publishing information about

barrier-free services they provide once they are given clear guidance - The Manuals on how

to create the Accessibility Guide (AG). Majority of the tourism providers from WAV preferred

hands-on assistance with production of the AG (on-site meeting of the facility’s manager with

a member of the project team, assistance with photo-documentation/following up The

Manual, transcription of data into AG format).This is still valid in RP5.

The AG approach might work on a wider scale if more providers in tourism take on this

concept and get into the habit of providing accessibility information as a standard service

offering strategy. AGs have been used in the tourism industry in the UK for years and can

help customers to explore barrier-free tourism destinations and assist businesses by tapping

into the growing market. This is still valid in RP5.

The aim is to get the AG concept in a wider community of local tourism providers - closer

alliance with the Tourism Authority South Moravia (CCRJM) - free Manuals available on their

website for the affiliated tourism business to utilize (about 50 tourism providers),

ZnojmoRegion and possibly CzechTourism? - all depends on how many AGs will be published

on websites of tourism businesses and the willingness of adoption of the AG approach on a

regional/national/international level. CCRJM has been supporting the AG approach and

promotes it via their online channels, e.g. Welcome guests with disabilities - it is easy.

Znojmo town is an associated partner in the project and they assisted in promoting the pilot

actions in the local newspaper Znojemské listy - January 2025 (page 10). In RP5, the project

team established a plan with the CCRJM on how to promote AGs in the tourism industry.

Firstly, tourism providers need to have instructional materials which enables them to

generate the AG. Online resource platform was built on the website of the largest national

database of wheelchair accessible places, VozejkMap. Many tourism providers already know

this application and, therefore, having the resources there makes sense. CCRJM is also going

to place all instructional materials on their website (summer 2025), as the local tourism

providers are used to going to the website for information.

In the Czech Republic, each region has its central tourism authority, equivalent to the CCRJM

in South Moravia. Managers of all these regional tourism authorities were contacted by

CCRJM and invited to our project webinar on the 10th June. At this webinar, AG was

introduced as a new approach in publishing accessibility information to allow travellers with

disabilities to plan travel hassle-free. All regional tourism authorities are managed by the

national tourism agency - CzechTourism. The project team established communication with

its representative and AG approach has been approved as a useful tool for promoting

accessible tourism in the country.

Page 44

Incorporating AG approach to an existing online platform of the Tourism Authority South

Moravia (CCRJM) - “Na jižní Moravu bez bariér” - some tourism venues advertised as barrier-

free fail to publish detailed information on accessibility (e.g. adapted toilets). This can be

rectified by publishing AGs of the advertised venues. Success depends on the willingness of

the tourism businesses to take an extra effort to create AGs etc. In RP5, a report on the

findings with recommendations for amendments was produced and communicated with the

representative of the CCRJM. We are expecting to see detailed accessibility information of

the listed barrier-free venues in the form of AG.

Personal communication with futurism facilities’ responsible personnel improves the

outcomes of the project pilot activities. In RP5, more tourism facilities from the pilot area

listed in WAV were contacted and AG were produced for those who showed an interest.

Personal communication and site-visits still remain the best approach, as we see it.

Page 45