## Tabelle1
Version 1 November 2023
OUTPUT FACTSHEET
Project index number | CE0100054 | Acronym | SUSTANCE
Output type ("x" to be included) | Strategy/ action plan |  | Pilot action | X | Solution
Output number (O.xx) | O.2.1 | Output title | Pilot actions promoting new /improved crossborder public transport rail services and innovative ICT tools for improving passenger mobility in CE
If the output target is > 1 in the AF, please specify the output(s) described in the factsheet | PA2 (Cross- border train connection HU-AT – Neusiedl am See-Fertőszentmiklós-Sopron)
Output delivery date | March 2025
Project website | https://www.interreg-central.eu/projects/sustance/
Summary description of the output Please present the output by addressing the following topics.
Territorial challenges and needs in the regions specifically addressed by the output (max. 700 characters)
The Lake Neusiedl area, in which the Pilot Action was implemented, is a border reigon with a strong peripheral character. During the times of the Cold War the border not only separated two nations, but also two geopolitical blocks; interaction across the “Iron Curtain” was very limited. On the Austrian side the Seewinkel was “locked” between the natural barrier of Lake Neusiedl on the one side and the border to Hungary on the other side. On the Hungarian side the city of Sopron had almost no “hinterland” to interact with. At the same time, the Lake Neusiedl/Fertő National Park and the city of Sopron attract many tourists and tourism is an important economic factor. This calls for sustainable mobility solutions addressing touristic needs. These mobility solutions should make use of the regional cross-border rail network and (also) target bicycle tourists, for which the region is popular due to its convenient topography.
Main aim(s) of the output and how it contributes to tackle the identified challenge(s) (max. 500 characters)
The pilot action addresses mainly two, partly interrelated, problems in the pilot region: Firstly, the market share for cross-border public transport between eastern Burgenland region (Seewinkel) and Western Hungary/Sopron area is rather low. Secondly, the rail transport offer between the Seewinkel and Sopron is today not very attractive. While it is possible today to travel by rail on this route, there is today always a change of trains required in Fertőszentmiklos. Train times in Fertsőszentmiklós are not always adjusted to each other and can either be rather long or very short (down to 3 minutes), with the latter situation causing risks of broken connections in case of train delays.
Technical description of the output (e.g. scope, main features, innovative elements etc.) (max. 1500 characters)
The Pilot Action consisted of an experimental, seasonal direct cross border train service between Sopron and Neusiedl am See via Ferstőszentmiklós (ca. 76 km). It was for the first time ever, that there was established a direct train service between Sopron and the Neusiedler Seebahn line. Two pairs of trains operated on weekends (Saturdays and Sundays) between 13 April and 25 August 2024. The train servuce primarily targeted tourist traffic and was operated using modern electric multiple units, offering the possibility of convenient bicycle transport. The key objectives or the Pilot Action are: - to improve the public transport offer between the Sopron on the Hungarian side and the Seewinkel on the Austrian side - to strengthen the attractiveness of public transport in particular for tourists and visitors
Involvement of target groups during output development and/or implementation (max. 700 characters)
In preparation of the Pilot Action, GYSEV analysed data from a market survey at the Fertőd (HU) - Pamhagen (AT) border crossing, giving a good understanding of the modal split as well as travel purposes. The survey revealed a high share of tourism-related trips across the border (about 1/3) and a very low share for rail (<2%). In the context of the Pilot Action six stakeholder consultations were held; three on the Hungarian side and three on the Austrian side, before, during and after the PIlot Action. I.a. actors from the tourism sector were invited and actively participated in the meetings. These stakeholder meetings confirmed an interest in the train service and resulted in constructive suggestions, how to further develop it. While these ideas could not be implemented within the scope of the project for both time and budgest reasons, they are taken into account in connection with discussions about a possible continuation of the traffic in the future or in a follow-up project. In particular, the idea of a Circle Train around entire Lake Neusiedl, as well as a possible extension to Vienna, attracted much interest. Further, tourism offices in the region were also provided with information leaflets about the train service and formed an important marketing channel.
Cooperation dimension of the output, i.e. joint development within the partnership and, if applicable, joint implementation (see output indicator definitions in chapter I.3.3 and Annex 2 of the programme manual) (max. 700 characters)
A co-design meeting with project partners was held in December 2023 to exchange experience in the preparation and implementation of the Pilot Action. Since another seasonal train service between Italy, Slovenia and Croatia was part of the project, this co-design exercise helped to better understand, tackle and solve challenges (e.g. related to vehicle authorisation and marketing). Further, bi-lateral meetings were continously held during the preparation and implementation phase with Associated Partner VOR (Public Transport Association in Burgenland/Eastern Austria). VOR contributed i.a. with integtration of the service in PT information tools and advertisement of the service.
Results - expected change and lasting effects in the territories generated specifically by the output, its uptake by relevant organisations and benefits for target groups (max. 1000 characters)
The KPIs defined for the Pilot Action were the following: KPI 1. Number of passengers using the service; KPI 2. Number of bicycles using the service; KPI 3. Willingness to discuss continuation of traffic after end of the project. The targets for all three KPIs were achieved. In case of KPI 1 and 2 the target values were clearly over-achieved; in particular, a very high share of passengers with bicycles (ca. 25%) was counted on the trains. Regarding KPI No. 3, discussions are on-going with relevant actors on both sides of the border, investigating a possible continuation of the train service respectively a possible follow-up project. It should be positively noted, that also in 2025 GYSEV ticket offices are receiving questions from potential passengers asking about the availability of tickets for the SUSTANCE/Lake Neusiedl train.
Ownership and durability of the output after the project end, considering financial and institutional support including, if applicable, maintenance (max. 700 characters)
Discussions for a possible continuation of the train service are on-going. This could also involve a modification of the service, i.a. with regard to the routing and traffic season. A renewed testing/demonstration of a modified service might be an option, before a more permanent solution might be established.
Transferability of the output to other territories, sectors or target groups and planned measures for supporting such transfer (max. 700 characters)
The train service tested under the Pilot Action could serve as a blue-print or inspire similar train services in other cross-border regions with a potential for or already developed tourism.
Related final deliverable(s) (Number(s) and title(s) to be included) | 2_D.2.2.2 PA2_Ex Post Report_Final_post consultation - GYSEV - CLEAN
Output web link (if applicable)
GPS coordinates (if applicable)